## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Set up the neccesary softwares | .25 | 2025-12-05 | Created an git repo, pushed a newly made unity project to it.
Maze renderer set up | 1.25 | 2025-12-05 | Wrote the maze renderer, responsible for "drawing" the wall/cell gameobjects at the correct place. After a lot of trial and error i settled on storing walls as an enum with the flags attribute. Trial included: Trying to store the entire maze in an bitpacked two dimenional byte array, attempting to store walls as 0's and cells as 1's, sadly this approach was visually not nice to look at, very efficient though. Will be using it in the future
Made the first algorithm | 1 | 2025-12-05 | Wrote the binary tree algorithm to test out the maze renderer. I settled for the binary tree algorithm as the first one to implement considering it Is one of the easiest to quickly learn. This allowed me to quickly test the maze renderer assuring it works before moving to any bigger algorithms | X
Recursive backtracker algorithm(also known as "depth first search") | 2 | 2025-12-06 | I started by reading all the wikipedia documentation on different maze types, I followed that by watching a video on different maze algorithms. I concluded that the Recursive backtracker would fulfill all the requirements set for the "perfect maze generation algorithm" as described in the pdf.
GPU-Instancing | 3 | 2025-12-08 | Performance was horrid: ~30 seconds when generating 250x250, 4 frames to render it. Thus I decided to fix it by using GPU instancing, a method I've used a few times before on big grids. Instead of spawning thousands of walls I store them as 4x4Matrices then send those directly to the gpu in batches of 1023. This allowed me to not having to use gameobjects(uneccessary bloat for memory) and be able to mass batch allowing me to reduce GPU communication and memory allocation.
Settings & UI | 2.5 | 2025-12-09 | For the requirements (those from the pdf) I needed to have the user be able to interact with the maze generator through ui. I first made direct communication between the sliders and the mazerenderer. Though it worked it was a mess of references and it only took one change on one of the gameobjects to break it all. So i made a "Settings" ScriptableObject to have a project-global access point to the settings allowing me to only needing to have one reference in all scripts needing to acess the settings.
Camera | 1 | 2025-12-10 | Seperated the camera behaviour from the maze generation. Additionally made it scale correctly for phones/ipads in builds
Growing tree algorithm | 1.5 | 2025-12-10 | Made the third and last algorithm, I decided to settle for the growing tree algorithm because of the huge difference from most algorithms. The growing tree algorithm doesn’t start at (~0, ~0), it starts at a random position in the maze, and instead of forming a snake-like path it instead carves long branches in the maze, allowing for some parts of the maze being hallways. | X
UI changes | 1 | 2025-12-10 | I let some of my friends give the generator a test run to get feedback, most of it was dedicated to the ugly ui. I got my UI/UX friend to brainstorm over the needed variables for the user, we settled on adding one: StepTime, allowing the user to instantly generate a maze or to watch it being generated. Additionally the previous ui scaled ugly on mobile so new sprites were made by: Robert Beltman(Credit required) and implemented to give the generator a smoother feel | X
Testing | .5 | 2025-12-10 | Did some last tests to see if my project was errorproof before handing it in. Discovered a few bugs: When putting a negative integer in the height or width boxes the generator would throw an error, fixed it by setting the value to 5 if it was <= 0. Additionally the time in between Steptime could be set to a number lower then 0. Which would error aswell, fixed by setting it to 0 if <= 0.
Readme | 0 |  | Added a readme, please read it.
Total amount of hours | 8